## Work Package Report
Project Name |  | Ion Therapy Research Facility |  |  |  | Financial Year |  | FY 2022 - 2023
WP Name |  | WP1.1 Project Mangement
WP# | Work Package Manager |  |  | C.Whyte J.Parsons |  | Report Date: |  | 2022-11-04
Project Start Date |  |  |  | Baseline Project End |  | Forecast Project End
2022-10-01 |  |  |  | 2024-09-30 |  | 2024-09-30
Approved Project Budget (£) |  |  |  |  | Estimate At Completion (£)
138000 |  |  |  |  | 138000
Progress
Progress to include tasks and milestones
No. | Task / Milestone | [5 empty] | Origional target date to complete | Current target date to complete | % complete
1 | Early review of progress towards CDR. WPM meetings all in place and operating to schedule. LhARA kick-off meeting in Liverpool completed14/11/2022. LhARA international review 26th/27th October completed. Feedback expected mid November. | [5 empty] | 2023-03-23 | 2023-03-23 | 17%
2 | Interim review of progress towards CDR | [5 empty] | 2023-09-21 | 2023-09-21 | 0%
3 | Early draft of LhARA CDR | [5 empty] | 2024-03-21 | 2024-03-21 | 0%
4 | Complete LhARA CDR. | [5 empty] | 2024-09-23 | 2024-09-23 | 0%
5 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
6 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
7 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
8 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
9 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
10 | [6 empty] | dd/mm/yy | dd/mm/yy | 0%
This Period Highlights
Next Period Forecast Highlights
Financial Summary - Total Project (£k) |  |  |  |  | Staff | Non-Staff |  | Total
Approved Total Funding |  |  |  |  | 128 | 10 |  | 138
Budgeted Cost to Date |  |  |  |  | 5.3 | 0.4 |  | 5.7
Actual Cost to Date |  |  |  |  | 5.3 | 0.4 |  | 5.7
Estimate at Completion |  |  |  |  | 128 | 10 |  | 138
Financial Summary - Current Financial Year (£k) |  |  |  |  | Staff | Non-Staff |  | Total
Approved FY Funding |  |  |  |  | 64 | 5 |  | 69
Budgeted Cost to Date (FY) |  |  |  |  | 5.3 | 0.4 |  | 5.7
Actual Cost to Date (FY) |  |  |  |  | 5.3 | 0.4 |  | 5.7
Estimate at End of Financial Year |  |  |  |  | 64 | 5 |  | 69
Estimate at Completion - Financial Year Distribution (£k) | [5 empty] | Total |  | 0
FY 1 |  |  | FY 2
0 |  |  | 0
Risks
Are there any new risks ?
No. | Risk Description |  |  |  | Risk Mitigation |  |  |  | Score
none
Issues
Are there any new isues ?
No. | Issue Description |  |  |  | Issue impact and status
none
Work Package Manager Additional Comments
none
Project Managers Supplementary Information

## Finance Dashboard (hidden)
Approved Total Funding: staff | Approved Total Funding: non staff | Approved Total Funding: total | Baseline Total Budgeted Cost: staff | Baseline Total Budgeted Cost: non staff | Baseline Total Budgeted Cost: total | Budgeted Cost to Date: staff | Budgeted Cost to Date: non staff | Budgeted Cost to Date: total | Actual Cost to Date: staff | Actual Cost to Date: non staff | Actual Cost to Date: total | Estimate at Completion: staff | Estimate at Completion: non staff | Estimate at Completion: total | Approved FY Funding: staff | Approved FY Funding: non staff | Approved FY Funding: total | Baseline FY Budgeted Cost: staff | Baseline FY Budgeted Cost: non staff | Baseline FY Budgeted Cost: total | Budgeted Cost to Date (FY): staff | Budgeted Cost to Date (FY): non staff | Budgeted Cost to Date (FY): total | Actual Cost to Date (FY): staff | Actual Cost to Date (FY): non staff | Actual Cost to Date (FY): total | Estimate at End of Financial Year: staff | Estimate at End of Financial Year: non staff | Estimate at End of Financial Year: total | Overall Rating | Number of open Red Risks | Number of open Amber Risks | Number of open Green Risks
128 | 10 | 138 | #REF! | #REF! | #REF! | 5.3 | 0.4 | 5.7 | 5.3 | 0.4 | #REF! | 128 | 10 | 138 | 64 | 5 | 69 | #REF! | #REF! | #REF! | 5.3 | 0.4 | 5.7 | 5.3 | 0.4 | 5.7 | 64 | 5 | 69
128000 | 10000 | 138000 | #REF! | #REF! | #REF! | 5300 | 400 | 5700 | 5300 | 400 | #REF! | 128000 | 10000 | 138000 | 64000 | 5000 | 69000 | #REF! | #REF! | #REF! | 5300 | 400 | 5700 | 5300 | 400 | 5700 | 64000 | 5000 | 69000 | #REF! | 0 | 0 | 0

## Risk Dashboard (hidden)
Ref | Risk Description | Risk Mitigation | Score | Risk or Issue
#REF! | #REF! | #REF! | #REF! | Risk
#REF! | #REF! | #REF! | #REF! | Risk
#REF! | #REF! | #REF! | #REF! | Risk
#REF! | #REF! | #REF! |  | Issue
#REF! | #REF! | #REF! |  | Issue
#REF! | #REF! | #REF! |  | Issue

## Milestone Dashboard (hidden)
Ref | Milestone Description | Baseline | Forecast | Variance | Comments | Major/Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Major
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Minor

## PRC Report - Colour Coded (hidden)
Project Name | [6 empty] | Status Date: |  | dd/mm/yy |  | Typically unchanged - updated only in exceptional circumstances
Project Ref |  |  | Department |  |  |  | Funding Source |  |  |  | Updated infrequently, only if impacted by project change
Project Manager |  |  | Project Sponsor |  |  |  | Overall Rating |  |  |  | Updated/refreshed monthly
Project Start Date |  |  | Baseline Project End |  |  |  | Forecast Project End |  |  |  | No input required - automatically updated by formula
dd/mm/yy |  |  | dd/mm/yy |  |  |  | dd/mm/yy |  |  |  | No input required - formula calculation with RAG formatting
Approved Project Budget (£k) |  |  | Baseline Project Budget (£k) |  |  |  | Estimate At Completion (£k)
0 |  |  | 0 |  |  |  | 0
Project Description
This Period Highlights / Next Period Forecast Highlights
Financial Summary - Total Project (£k) |  |  |  |  | Staff |  | Non-Staff |  | Total
Approved Total Funding |  |  |  |  | 0 |  | 0 |  | 0
Baseline Total Budgeted Cost |  |  |  |  | 0 |  | 0 |  | 0
Budgeted Cost to Date |  |  |  |  | 0 |  | 0 |  | 0
Actual Cost to Date |  |  |  |  | 0 |  | 0 |  | 0
Estimate at Completion |  |  |  |  | 0 |  | 0 |  | 0
Financial Summary - Current Financial Year (£k) |  |  |  |  | Staff |  | Non-Staff |  | Total
Approved FY Funding |  |  |  |  | 0 |  | 0 |  | 0
Baseline FY Budgeted Cost |  |  |  |  | 0 |  | 0 |  | 0
Budgeted Cost to Date (FY) |  |  |  |  | 0 |  | 0 |  | 0
Actual Cost to Date (FY) |  |  |  |  | 0 |  | 0 |  | 0
Estimate at End of Financial Year |  |  |  |  | 0 |  | 0 |  | 0
Estimate at Completion - Financial Year Distribution (£k) | [6 empty] | Total |  | 0
FY 1 |  | FY 2 |  |  | FY 3 |  |  | FY 4
Past FY |  | Past FY |  |  | Past FY |  |  | Current FY
FY 5 |  | FY 6 |  |  | FY 7 |  |  | FY 8
Future FY |  | Future FY |  |  | Future FY |  |  | Future FY
Major Milestones Summary (key project stages and major deliverables)
Ref | Milestone Description |  |  | Baseline | Forecast | Variance | Comments
0
0
0
0
0
0
0
0
Minor Milestones Summary (6-month lookahead)
0
0
0
0
0
0
0
0
Risk and Issue Summary | [6 empty] | Risk Trend
Number of open Risks by RAG Status (post mitigation scoring):
RED |  |  | AMBER |  |  |  | GREEN
Top 3 Risks (post mitigation score)
Ref | Risk Description |  |  |  | Risk Mitigation |  |  |  |  | Score
Top 3 Issues
Ref | Issue Description |  |  |  | Impact and Status
Project Managers Supplementary Information
Project Managers Supplementary Information
Formulas:
Variance = NETWORKDAYS([Baseline],[Staff])

## STFC Project Report - Example (hidden)
Project Name |  | ESS Beam Transport Modules UK-A-6 | [5 empty] | Status Date: |  | 2019-03-31
Project Ref |  | 1224 |  | Department |  | Technology |  | Funding Source |  | BEIS
Project Manager |  | P. Aden |  | Project Sponsor |  | N. Geddes |  | Overall Rating |  | Amber
Project Start Date |  |  |  | Baseline Project End |  |  |  | Forecast Project End
2015-09-01 |  |  |  | 2019-10-30 |  |  |  | 2020-12-31
Approved Project Budget (£k) |  |  |  | Baseline Project Budget (£k) |  |  |  | Estimate At Completion (£k)
7989.999 |  |  |  | 7613.999 |  |  |  | 6521.13
Project Description
The main package in this scope is the Linac Warm Units (LWUs) which consists of 73 LWUs, 54 beam pipe units, 2 prototype units, 3 dummy chambers, and 4 cleanroom assemblies. The scope of work includes the design, procurement and assembly of vacuum equipment, vacuum chambers, beam pipes and support structures. It also includes magnet, BPM and BCM integration; it does not include design or procurement of the magnets, BPMs, BCMs, or any diagnostic equipment. Magnets and BPMs will be supplied to the STFC on contract loan from ESS for assembly into the LWUs.
This Period Highlights / Next Period Forecast Highlights
Magnets and LWU vacuum vessels have now been delivered to DL, marking the start of the build phase for the LWUs. They were expected to arrive at DL at the end of January at DL, and have resulted in the need for a change request to be generated to realign the milestones set out in the TA. This delay presents a risk that the clean room may still be occupied in March 2020 which will have an impact on the commencement of the Hi Lumi assembly phase. At Lund, the Beam Pipe Delivery @ ESS and Installation continues. The project has now delivered 204m of 480m of the accelerator. The main bulk of work (LWUs) that started in Jan-19 with the arrival of the first Quads continues. All particulate counted dummy cryo modules were completed in March-19. The first batch of Mobile Cleanrooms were delivered to ESS in this period, with the rest following before the end of 2019. This first unit will be installed and brought into operation in November, this will allow ESS to begin particle free installation in the tunnel! In the next period, focus is on the design of the dogleg, and dipole regions. This area is a 4 degree include with a trench cut into it on the flat. This region is particularly difficult as space is very constrained, and with the weight of the magnets (up to 5 Tonnes) and lack of available craneage also being a constraint, successful installation design is key.
Financial Summary - Total Project (£k) | [5 empty] | Staff |  | Non-Staff |  | Total
Approved Total Funding | [5 empty] | 1999.385 |  | 5990.614 |  | 7989.999
Baseline Total Budgeted Cost | [5 empty] | 1905.296 |  | 5708.703 |  | 7613.999
Budgeted Cost to Date | [5 empty] | 901.5 |  | 2701.1 |  | 3602.6
Actual Cost to Date | [5 empty] | 941.6 |  | 2826.1 |  | 3767.7
Estimate at Completion | [5 empty] | 1631.821 |  | 4889.309 |  | 6521.13
Financial Summary - Current Financial Year (£k) | [5 empty] | Staff |  | Non-Staff |  | Total
Approved FY Funding | [5 empty] | 560.353 |  | 1678.946 |  | 2239.299
Baseline FY Budgeted Cost | [5 empty] | 438.893 |  | 1315.026 |  | 1753.919
Budgeted Cost to Date (FY) | [5 empty] | 262.4 |  | 934.3 |  | 1196.7
Actual Cost to Date (FY) | [5 empty] | 256.4 |  | 1237.2 |  | 1493.6
Estimate at End of Financial Year | [5 empty] | 401.69 |  | 1203.558 |  | 1605.248
Estimate at Completion - Financial Year Distribution (£k) | [7 empty] | Total |  | 6521.13
FY 14/15 |  |  | FY 15/16 |  |  | FY 16/17 |  |  | FY 17/18
8.15 |  |  | 195.8 |  |  | 611.61 |  |  | 1289.21
FY 18/19 |  |  | FY 19/20 |  |  | FY 20/21 |  |  | FY 21/22
1605.25 |  |  | 1793.73 |  |  | 1017.38 |  |  | 0
Major Milestones Summary (key project stages and major deliverables)
Ref | Milestone Description |  |  |  | Baseline | Forecast | Variance | Comments
1 | Conception Stage - Project Start Date |  |  |  | 2015-09-01 | 2015-09-01 | 1 | Complete
2 | Definition Stage - PMP Completed |  |  |  | 2016-11-01 | 2016-11-01 | 1 | Complete
3.1 | Implementation Stage - Design Complete |  |  |  | 2017-10-30 | 2019-05-12 | 400 | Issues at MEGA leading to late completion of Design
3.2 | Implementation Stage - All Procurement Complete |  |  |  | 2018-04-20 | 2020-09-28 | 637 | Issues at MEGA causing delay to procurement
3.3 | Implementation Stage - All Hardware delivered |  |  |  | 2019-09-15 | 2020-11-30 | 316 | Forecast MEGA deliveries
4 | Closure Stage - Project Closure Report Complete |  |  |  | 2019-10-30 | 2020-12-31 | 307 | Forecast late completion due to issue with Magnet supplier.
0
0
Minor Milestones Summary (6-month lookahead)
3.2.9 | QTY 57 x Beam Pipe Units |  |  |  | 2019-07-30 | 2019-07-30 | 1
0
0
0
0
0
0
0
Risk and Issue Summary | [7 empty] | Risk Trend |  | Static
Number of open Risks by RAG Status (post mitigation scoring):
2 |  |  |  | 6 |  |  |  | 8
Top 3 Risks (post mitigation score)
Ref | Risk Description |  |  |  |  | Risk Mitigation |  |  |  |  | Score
12 | As a result of design issues at MEGA (see CDR), there is a risk that hardware delivery will not be achieved to baseline dates. |  |  |  |  | Close communication with ESS magnet group to ensure latest magnet delivery dates are accurate. |  |  |  |  | 25
22 | As a result of late design information from *supplier*, there is a risk that the clean room hardware will not be at ESS to schedule |  |  |  |  | Review supply chain with supplier and look for alternative suppliers. |  |  |  |  | 20
8 | As a result to changes in the ESS Programme, there is a risk that target completion dates will be changed |  |  |  |  | Communicate related issues to the ESS programme team and ensure that the programme change control process is clear. |  |  |  |  | 12
Top 3 Issues
Ref | Issue Description |  |  |  |  | Impact and Status
1 | Paint curing issues at the steelwork supplier led to a rework programme in order to prevent reputational harm to STFC with ESS |  |  |  |  | Steelwork delivery was 4 weeks late to the current schedule but this was agreed with the ESS installation team and able to be managed.
Project Managers Supplementary Information
Project Managers Supplementary Information
Formulas:
Variance = NETWORKDAYS([Baseline],[Technology])