## Sheet1
PoPLaR Checklist:
Pre-experiment 1 (alignment) Checklist: | Pre-experiment 2 (radiobiology) Checklist:
Equipment Design & Procurement: | Beamline Modelling:
PMQ XYZ stages (5-7 weeks) | Remodel based on information from experiment 1
Cell station vacuum parts (4 weeks)
Oxford cell station | Radiobiology Preparation:
Thin window | Experiments on Birmingham cyclotron for comparison
Collimator/s | Prepare 54 dishes- thaw FaDu/HeLa and irradiate (7 days before)
PMQ clamping system
Source Characterisation:
Beamline Modelling: | Laser Beamline alignment (0.5 days)
Understand PMQ tilt and misalignment sensitivities | Source optimisation with PMQs (1 day)
Understand source misalignment | Dosimetry and source stability measurements (2 days)
Determine PMQ configuration
Determine PMQ positioning | Radiobiology Experiment:
Seed (night before) & irradiate (morning)
Assembly & Alignment: | Stain colonies 7-10 days later, process clonogenic information (2 weeks)
Construction of the cell station and updated TP beamline | Need 2 weeks between beam time (March & April?) to find issues, 2-3 repeats in next session
Definition of an offline alignment line
Construction and offline alignment of PMQ setup
Install of PMQ system in vacuum chamber
Source Characterisation:
Laser Beamline alignment (0.5 days)
Source optimisation w/o PMQ (0.5 days)
PMQ transmission, activation and debris test (0.5 days)
Lanex/beam profiler measurement at end of beamline (1 day)
PMQ position optimisation (0.5 days)
RCF measurements through beamline (0.5 days)
Full cell assembly RCF measurement (0.5 days)