## Sheet1
Date: | 2021-10-11 | Issue | 2
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Staff FTE by financial year; quarters are noted for calendar year
Years | Staff | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | Total |  | 2022/23 |  |  |  | 2023/24 |  |  |  | 2024/25 |  |  |  | 2025/26 |  |  |  | 2026/27
Flag |  | Fraction | Fraction | Fraction | Fraction | Fraction | Fraction |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1
Task | Project office support
Institute | Imperial Physics
Staff | IC-Phys-Support-1 | 1 | 1 | 1 | 1 | 1 | 5 | bar: 2022/23 Q2 to 2026/27 Q1
Institute | Bio/Med - WP5
Void |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Institute | Strathclyde Physics | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | Strathclyde-Phys-Stf-1 | 1 | 1 | 1 | 1 | 1 | 5 | bar: 2022/23 Q2 to 2026/27 Q1
Institute | STFC
Staff | STFC-Finance-Support | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
RiskMitigationStaff | Risk mitigation effort | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EndStaff | Staff totals | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 11
NonStaffHd | Non staff | £k | £k | £k | £k | £k | 1320
Task | Project office support
Equipment | Collaboration meetings - 3 per year | 15 | 15 | 15 | 15 | 15 | 75
Void | [6 empty] | 0
EquipEnd | Sub-total | 15 | 15 | 15 | 15 | 15 | 75
RiskMitigationEquip | Cost of risk mitigation (equipment) | 0 | 0 | 0 | 0 | 0 | 0
TotalEquip | Eqipment total | 15 | 15 | 15 | 15 | 15 | 75
Consume | Consumables | 10 | 10 | 10 | 10 | 10 | 50
Travel | Travel | 15 | 15 | 15 | 20 | 20 | 85
OtherNonStaff | PPI, engagement, and outreach | 10 | 10 | 10 | 10 | 10 | 50
OtherNonStaff | Patient representative and other seconded advisor expenses | 6 | 6 | 6 | 6 | 6 | 30 | Will need appropriate justification. 2 people inc travel/subs, 2x per year plus ??
OtherNonStaff | Review-committee expenses | 5 | 5 | 5 | 5 | 5 | 25 | 2 people inc. travel/subs, 2x per year
NonStaffEnd | Total non-staff costs | 61 | 61 | 61 | 66 | 66 | 315
Non-staff costs include VAT but not inflation.
[6 empty] | Total | 1635
Update history
2021-10-15 | CW: adjust non-staff costing
2021-10-11 | KL: Add jason to WPM; minor formatting updates; introduce "void" flag to allow white space; update to patient representative field, Meetings flag changed back to equiment
2021-10-08 | CW- add Patient Rep costs 2@£5ea. /yr
2021-09-27 | CW- move outreach to WP5, apply 120k/FTE. Add total
2021-09-14 | CW: Update staff designations
2021-09-14 | KL: Added back first year, added PPI etc., tidied formatting, averaging and addition.
2021-09-13 | CW: first attempt to add content
2021-07-20 | First version